AUTHORITATIVE SUPPORTING PRODUCTION DOCUMENTATION STANDARD & CONTROL REGISTER

Single Source of Truth (SSOT) — Six-Set Performance

Revision 1.0 — Synthesis Baseline

CONTROLLED STANDARD — governs the supporting production-document system

Prepared July 19, 2026

Source lineage: set01.txt • set02.txt • supportingdocuments01.txt • supportingdocuments02.txt

# 1. Purpose and Authority

This document is the authoritative specification for all production documents supporting the Authoritative Show Control & Performance Cue Book (“Doc 1”). Doc 1 alone governs program-event order, supplied durations, planned timing profiles, and PGM/TECH/FIN identities. Supporting documents govern department implementation, safety, logistics, readiness, and historical records.

Core SSOT rule — Supporting documents reference Doc 1 IDs rather than creating independent competing versions of the show sequence. Convenience labels may be displayed, but the controlled identity and timing source remains Doc 1.

# 2. Controlled-Document Architecture

| Level | Documents | Role |
| --- | --- | --- |
| Level 1 — Core authority | Doc 1; this standard; CTRL-01; SAFE-01 | Defines show identity/timing, documentation rules, current revisions, and safety authority. |
| Level 2 — Operational documents | Stage management and all department plans/cue sheets/checklists | Defines how the approved show is executed. |
| Level 3 — Records | Rehearsal/performance reports, asset verification, maintenance, incidents, archives | Records what occurred and tracks action/closure without silently changing the approved show. |

## 2.1 Common control rules

1. Every controlled file carries a Document ID, production name, revision, status, effective date, owner, approver, and Doc 1 revision/profile reference.

2. Recommended filename: [Production]_[DocumentID]_[ShortTitle]_rMAJOR.MINOR_[YYYY-MM-DD].ext.

3. Only APPROVED files may be used for performance. DRAFT, IN REVIEW, SUPERSEDED, and ARCHIVED files must be unmistakably labeled.

4. A major revision changes sequence, duration, safety, equipment mode/routing, or responsibility. A minor revision refines operational cue detail. A patch revision corrects non-operational text.

5. Data is owned once. PGM title/order/duration resides in Doc 1; supporting documents reference the PGM ID and may show a synchronized label only for readability.

6. Safety conflicts are resolved in favor of the safer approved restriction, followed by formal change propagation.

7. Observations and suggestions remain records until approved. A rehearsal or performance report never silently changes the show.

# 3. Master Controlled-Document Register

| ID | Controlled document | Owner / accountable lead | Authoritative purpose |
| --- | --- | --- | --- |
| CTRL-01 | Document Control Register and Cue Revision Log | Production Manager / Stage Manager | Controls document IDs, owners, status, revision, approval, distribution, supersession, and change history. |
| SM-01 | Stage Manager’s Calling Script | Stage Manager / Show Caller | Exact ordered execution script containing standbys, warnings, GO calls, confirmations, holds, aborts, entrances, exits, safety cues, and approved changes. |
| SM-02 | Run of Show and Event-Day Operating Schedule | Stage Manager / Production Manager | Simplified operational overview from crew call through load-out, including sets, songs, transitions, checks, doors, performance, bows, audience exit, reset, and teardown. |
| AUD-01 | Audio Playback, Microphone, Monitor, and Recovery Sheet | Audio Lead | Authoritative audio implementation: files, versions, durations, devices, routing, levels, microphones, monitoring, start/stop modes, fades, backups, and recovery. |
| LX-01 | Lighting Cue List | Lighting Lead | Lighting cue numbers, looks, triggers, fade/follow times, fixture groups, colors, positions, movement, blackouts, audience looks, warnings, overrides, and emergency looks. |
| LX-02 | DMX Patch, Universe, Network, and Control Plan | Lighting Lead / Technical Director | Fixture modes and addresses, universes, network nodes, wireless settings, power sources, control configuration, patch backups, and test status. |
| VID-01 | Video, Projection, and LED Media Cue List | Video Lead | Media files, resolutions, aspect ratios, destinations, layers, masks, loops, holds, triggers, fades, fail states, screen-drop coordination, and backups. |
| STG-01 | Stage Plot and Backstage Safety Map | Technical Director / Stage Manager | Scaled or clearly dimensioned overhead plan of stage, equipment, performance positions, traffic routes, cable paths, quick changes, props, emergency exits, and fire lanes. |
| DECK-01 | Deck, Preset, and Scene-Change Plot | Deck Lead | Who moves or presets each item, route, timing, spike marks, handoffs, clearances, confirmation signals, reset, and contingency. |
| AUTO-01 | Rigging and Automation Cue and Safety Sheet | Automation/Rigging Lead | Platform, screen, flown, motorized, and mechanical movements with limits, loads, operators, spotters, interlocks, E-stops, aborts, and recovery. |
| WARD-01 | Wardrobe Plot and Quick-Change Sheets | Wardrobe Lead | Every costume and piece by performer and set, presets, locations, dressers, time available, change sequence, fastening preparation, checks, repairs, laundry, reset, and backup plan. |
| PERF-01 | Performer Track Sheets | Stage Manager / Director | Individual entrance, exit, blocking, route, costume, prop, microphone, instrument, position, cue, responsibility, clear-zone, and bow information. |
| PROP-01 | Props and Performer Equipment Tracking Sheet | Props/Deck Lead | Preset, inspection, user, handoff, onstage position, removal, return, consumables, reset, missing/damaged procedure, and accountable person. |
| FX-01 | Special-Effects Cue and Safety Sheet | Effects Lead / Safety Authority | Fog, haze, strobe, flame, pyro, sparks, confetti, cryogenic, loud report, breakaway, lift, and machinery cues with zones, approvals, permits, fire watch, shutdown, and cleanup. |
| SAFE-01 | Safety, Emergency, Contingency, and Show-Stop Plan | Production Manager / Venue Safety Authority / SM | Emergency-stop authority, evacuation, fire, medical, severe weather, power/system failures, missing performer, effect misfire, hold/restart/cancel criteria, contacts, and incident reporting. |
| COMMS-01 | Communications and Headset Plan | Stage Manager / Communications Lead | Headset and radio assignments, channels, call signs, cue-light meanings, recipients, hold authority, backup methods, and emergency communications. |
| PWR-01 | Power Distribution and Shutdown Plan | Technical Director / Electrician | Circuits, loads, dimmers, distribution, isolation, grounding, cable routes, protection, backup power, energization, and shutdown order. |
| VEN-01 | Venue Advance and House Interface Document | Production Manager / Venue Representative | Stage and access dimensions, load-in route, rigging points, power, dressing rooms, staffing, house equipment, curfew, sound limits, permits, restrictions, and contacts. |
| SCHED-01 | Load-In, Rehearsal, Performance, and Load-Out Schedule | Production Manager | Arrival and call times, setup sequence, focus, soundcheck, system tests, rehearsal, meal/rest periods, doors, show, teardown, vehicle movement, and departure. |
| CHECK-01 | Department Preset, Pre-Show, Post-Show, and Shutdown Checklists | Stage Manager / Department Leads | Initialed readiness and closure checklists for stage, automation, audio, lighting, video, wardrobe, props, instruments, FX, backstage, house, emergency equipment, and post-show safety. |
| CONTACT-01 | Contact Sheet and Responsibility Matrix | Production Manager | Names, roles, phones, emails, call signs, radio assignments, emergency contacts, alternates, approval authority, and RACI responsibilities. |
| REP-01 | Rehearsal Report | Stage Manager | Timing changes, missed cues, technical problems, injuries, decisions, assignments, owners, due dates, and distribution from each rehearsal. |
| REP-02 | Daily Performance Report | Stage Manager | Actual times, attendance, late start, cue and equipment problems, substitutions, performer/wardrobe/prop notes, incidents, maintenance, changes, notifications, and next-show actions. |
| ASSET-01 | Show Asset, File, Version, Checksum, and Backup Manifest | Production Manager / Department Leads | Central index of every playback, video, lighting, console, show-control, document, and configuration asset, including approved version, checksum, location, backup, and restore test. |
| MAINT-01 | Equipment Inspection, Maintenance, Damage, and Near-Miss Log | Technical Director / Production Manager | Open defects, inspection results, repair status, tag-out decisions, recurring faults, damage, near misses, responsible owner, due date, verification, and closure. |

# 4. Common Header and Record Schema

Every controlled document should begin with the following identity block:

Production; venue; performance/rehearsal date or applicability.

Document ID and title; revision and status; prepared by; owner; approved by; effective date.

Referenced Doc 1 revision and active timing profile.

Confidentiality/distribution classification; page X of Y; supersedes; controlled storage location and backup.

Every cue, task, movement, asset, or item record should use the applicable subset of these fields:

Unique record ID and PGM/TECH/FIN reference.

Department cue/item ID; event/item name; planned time; exact trigger.

Prerequisite or clearance; action; responsible operator; standby recipients; completion signal.

Normal result; failure state; HOLD/ABORT/recovery; safety zone and authority.

Asset/equipment reference; revision; approval/status; notes.

# 5. Detailed Controlled-Document Specifications

## CTRL-01 — Document Control Register and Cue Revision Log

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Establishes which files are controlled, current, approved, distributed, superseded, and archived. It is the governance index for the entire production-document set. | Production Manager is accountable; Stage Manager maintains show-cue revisions; each department lead maintains its document entries. | Production title and IDs; Doc 1 active revision; department document submissions; approval decisions; distribution list. |

Minimum required content

Document ID, title, scope, owner, editor, approver, status, revision, effective date, last modified date, storage location, backup location, and recipients.

Change entry: revision number, date, affected cue/document, previous instruction, new instruction, reason, requested by, approved by, departments notified, implementation date, and verification result.

Superseded version location and explicit withdrawal confirmation so operators do not use mixed revisions.

Production-level decision log for unresolved SSOT items and the date each is resolved.

Approval / completion criteria

Every controlled document appears exactly once in the register.

All performance operators confirm the same approved revision before places.

No change is considered effective until approved, propagated, and verified.

Synchronization rule: References every controlled document and Doc 1 cue/event IDs. It is updated whenever any controlled document changes.

## SM-01 — Stage Manager’s Calling Script

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Transforms the master program sequence into the exact words and moments the show caller uses to execute the performance. | Stage Manager/Show Caller; approved by Production Manager and Director; safety cues also approved by the responsible technical/safety authority. | Doc 1 active timing profile and cue registry; every department cue list; performer tracks; emergency plan. |

Minimum required content

Every warning, standby, GO, confirmation, completion, hold, abort, blackout, house-light, performer entrance/exit, scene movement, wardrobe readiness, and safety cue in exact order.

Exact trigger stated as lyric, musical count, action, visual condition, timecode, or explicit authorization—not merely “near the end.”

Cue number crosswalk to PGM/TECH/FIN IDs and department cue numbers.

Approved alternate/contingency calls, restart points, recovery instructions, and emergency pages.

Revision identifier in header/footer of every page and a conspicuous active timing profile.

Approval / completion criteria

No TBD trigger remains for any live cue.

Caller and operators complete at least one cue-to-cue rehearsal from the same revision.

All safety-critical calls are unambiguous and have confirmation language.

Synchronization rule: Doc 1 governs sequence and planned timing; department sheets govern implementation; SAFE-01 governs emergency authority.

## SM-02 — Run of Show and Event-Day Operating Schedule

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Provides the concise operational map of the full event day and performance flow. | Stage Manager with Production Manager. | SCHED-01, Doc 1, venue/FOH details, department calls. |

Minimum required content

Crew calls, load-in/setup milestones, system checks, soundcheck, lighting focus/checks, video checks, costume/prop checks, performer call, house open, places, show start, set sequence, transitions, breaks/encore holds, bows, audience exit, reset, and load-out.

Planned clock time, responsible owner, location, prerequisite, and status for each milestone.

Estimated real-world duration distinct from pure music runtime.

Approval / completion criteria

All departments can understand the day without reading the calling script.

Clock times match SCHED-01 and sequence matches Doc 1.

Synchronization rule: References Doc 1 PGM/TECH/FIN IDs; does not duplicate detailed technical instructions.

## AUD-01 — Audio Playback, Microphone, Monitor, and Recovery Sheet

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Defines every audio action and the tested recovery path. | Audio Lead. | Doc 1; approved audio assets from ASSET-01; performer needs; venue system details. |

Minimum required content

Audio cue number, PGM/TECH/FIN relation, track title, exact filename, approved version/edit, duration, sample rate, bit depth, channel format, checksum, storage path, and backup path.

Playback computer/device, application/session, output assignment, routing, start mode, stop mode, fade-in/out, follow behavior, target level, and authorization.

Microphone, DI, instrument, monitor wedge, and in-ear assignments; spare channels and batteries.

Primary and backup playback systems, switchover method, recovery/restart point, operator call, and failure-state behavior.

Approval / completion criteria

Every file audibly verified and duration reconciled with Doc 1.

Backup playback tested under realistic failure conditions.

No ambiguous duplicate filenames or unlabeled alternate edits.

Synchronization rule: Updates ASSET-01; supplies department cues to SM-01; duration changes require Doc 1 revision.

## LX-01 — Lighting Cue List

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Defines the visual lighting sequence and safe operator actions. | Lighting Lead. | Doc 1; stage plot; patch plan; director/design approvals; FX warnings. |

Minimum required content

LX cue number, associated PGM/TECH/FIN ID, exact trigger, look/scene description, fade time, delay/follow time, hold behavior, and operator notes.

Intensity, color, fixture groups, focus/position, movement, beam effects, followspot instructions, audience looks, blackouts, and work/emergency looks.

Strobe and photosensitivity warnings, duration/frequency limits where applicable, manual overrides, and console-failure procedures.

Approval / completion criteria

All looks programmed, labeled, backed up, and rehearsed.

Cue triggers match SM-01 and fixture groups match LX-02.

Emergency and work-light states are immediately accessible.

Synchronization rule: References LX-02 and ASSET-01; sends cue numbers/calls to SM-01.

## LX-02 — DMX Patch, Universe, Network, and Control Plan

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Makes the control and addressing system reproducible and serviceable. | Lighting Lead; Technical Director approves power/network interfaces. | Fixture inventory; stage plot; power plan; console/network design. |

Minimum required content

Fixture manufacturer/model, quantity, channel mode, fixture ID, DMX address, universe, network node/port, wireless transmitter/receiver and settings.

Power source/circuit, dimmer or relay behavior, safety channel restrictions, RDM settings where used, and physical location.

Console show-file version, software/firmware versions, IP/network configuration, backups, patch printout, and verification status.

Approval / completion criteria

No address conflicts; all fixtures respond in the intended mode.

Patch and console file match and are backed up.

Power assignment reconciles with PWR-01.

Synchronization rule: Referenced by LX-01, PWR-01, STG-01, and ASSET-01.

## VID-01 — Video, Projection, and LED Media Cue List

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Defines every visual-media action, destination, failure state, and backup. | Video Lead. | Doc 1; approved media from ASSET-01; screen/rigging details; venue video system. |

Minimum required content

Video cue number, PGM/TECH/FIN ID, exact filename, version, checksum, codec, resolution, frame rate, aspect ratio, duration, and storage/backup location.

Playback machine, software/session, output/screen destination, layer, mask, scaling/cropping, start/stop trigger, fade, loop, hold, and blackout frame.

Fallback image/state if playback fails and screen-drop coordination requirements.

Approval / completion criteria

Every asset is frame-checked on the actual output path.

Fail states and backups are tested.

Screen movement and media timing are rehearsed together.

Synchronization rule: Updates ASSET-01; coordinates with AUTO-01; supplies cues to SM-01.

## STG-01 — Stage Plot and Backstage Safety Map

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Provides the shared spatial truth for staging, equipment, traffic, and safety. | Technical Director; Stage Manager verifies traffic/safety data. | Venue dimensions; design; equipment lists; performer blocking; emergency plan. |

Minimum required content

Stage dimensions, centerline, plaster line or reference line, trim/heights where relevant, audience edge, wings, entrances, exits, and backstage routes.

Platforms, risers, stairs, ramps, railings, scenic pieces, screen, microphones, monitor wedges, instruments, amplifiers, lighting towers, fog/FX devices, prop tables, quick-change areas, and performance positions.

Cable paths, floor protection, spike marks, restricted/clear zones, automation travel, emergency exits, fire lanes, extinguishers, and first-aid/AED location where supplied by venue.

Approval / completion criteria

Drawing is dimensioned or explicitly not to scale.

All departments sign off that their equipment and safety zones are accurately represented.

Revision date matches physical setup.

Synchronization rule: Referenced by DECK-01, AUTO-01, PWR-01, LX-02, PERF-01, WARD-01, PROP-01, FX-01, and SAFE-01.

## DECK-01 — Deck, Preset, and Scene-Change Plot

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Defines repeatable, assigned movement and preset work onstage and backstage. | Deck Lead / Assistant Stage Manager. | Doc 1; stage plot; props; performer tracks; automation plan. |

Minimum required content

Item, cue/event ID, preset location, spike mark, responsible person, movement route, start condition, end position, handoff point, timing, clearance check, and completion signal.

Reset route and post-show location; contingency for blocked route, missing crew, or failed item.

Distinction between manual deck movement and AUTO-controlled movement.

Approval / completion criteria

Every move is assigned and rehearsed.

Routes do not conflict with performers, quick changes, cables, FX zones, or automation travel.

Synchronization rule: Supplies movement confirmations to SM-01; references STG-01, PROP-01, PERF-01, and AUTO-01.

## AUTO-01 — Rigging and Automation Cue and Safety Sheet

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Controls every powered, flown, dropped, lifted, or otherwise safety-critical movement. | Automation/Rigging Lead; Technical Director and venue authority approve. | Doc 1 TECH cues; engineered/venue rigging data; stage plot; safety plan. |

Minimum required content

Cue number and related TECH/PGM ID, equipment, starting/ending position, direction, speed, travel distance, trim/limits, load rating, motor/controller, operator, spotter, and exact trigger.

Pre-move performer-clear and area-clear confirmations; safety interlocks; E-stop locations; abort language; stop behavior; manual rescue/recovery procedure; post-move confirmation.

Inspection/test record, competent-person approval, venue/engineering approval, and restrictions.

Approval / completion criteria

No movement is called without positive clearance.

Limits, interlocks, and E-stops tested before each performance.

Failure and stopped-move recovery rehearsed without exposing performers to risk.

Synchronization rule: TECH-001 and TECH-003 are completed here; supplies exact calls to SM-01; coordinates with SAFE-01 and STG-01.

## WARD-01 — Wardrobe Plot and Quick-Change Sheets

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Makes every costume state and quick change repeatable. | Wardrobe Lead. | Doc 1; director/design decisions; performer tracks; schedule. |

Minimum required content

Performer, production block, costume look, every garment/accessory, labeling, preset location, changing location, dresser, and inspection status.

Available change time, exit cue, re-entry cue, route, removal/addition order, fastening sequence/preparation, microphone/instrument coordination, and readiness signal.

Backup pieces, delay contingency, emergency repair, laundry, drying, maintenance, inventory, and reset responsibilities.

Approval / completion criteria

Every quick change is timed and rehearsed.

A named person gives the readiness confirmation.

Backup plan exists for damaged/missing pieces and delayed changes.

Synchronization rule: PGM-006/TECH-002, PGM-011, and PGM-016 are fully defined here; syncs with PERF-01 and SM-01.

## PERF-01 — Performer Track Sheets

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Gives each performer a concise, individual track through the entire show. | Stage Manager/Director; performer acknowledges. | Doc 1; blocking; stage plot; wardrobe; props; audio assignments. |

Minimum required content

Starting position, places call, entrance/exit cue, wing/route, onstage position, platform/stair use, movement restrictions, microphone/instrument pickup and return, prop handoffs, costume state/change route, and special responsibility.

Areas to keep clear for automation/scenic movement and FX; emergency/hold behavior; final bow position.

Contact/check-in and understudy/substitution notes where applicable.

Approval / completion criteria

No performer route conflicts with safety zones or crew moves.

Each performer reviews and rehearses the track.

Synchronization rule: References STG-01, WARD-01, PROP-01, AUD-01, AUTO-01, FX-01, and SM-01.

## PROP-01 — Props and Performer Equipment Tracking Sheet

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Controls every prop and performer-operated item from inspection through reset. | Props Lead / Deck Lead. | Doc 1; stage plot; performer tracks; design/FX decisions. |

Minimum required content

Item ID/name, description, inspection criteria, starting preset, user, responsible crew, pickup/handoff cue, onstage position, return/removal cue, post-show location, and reset procedure.

Consumable quantity per performance, minimum stock, replenishment owner, cleaning/sanitation, safe handling, and storage.

Missing, damaged, unsafe, or substituted item procedure and approval authority.

Approval / completion criteria

Every item is accounted for before and after the show.

Weapon-themed, breakaway, liquid, flame-related, or hazardous props have specific safety controls.

Synchronization rule: Supplies handoffs to PERF-01/DECK-01/SM-01; safety-sensitive items also appear in SAFE-01 or FX-01.

## FX-01 — Special-Effects Cue and Safety Sheet

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Controls all special effects as both cues and regulated hazards. | Effects Lead; Safety Authority and venue/fire authority approve where required. | Doc 1; stage plot; venue rules; permits; risk assessment; manufacturer instructions. |

Minimum required content

Effect type: fog, haze, strobe, flame, pyrotechnics, sparks, confetti, streamers, CO₂/cryogenic, loud report, breakaway, blood/liquid, machinery, performer flying/lift, or other.

Cue ID, exact trigger, operator, device/material, quantity/settings, duration, exclusion zone, performer/audience clearances, ventilation, warning/advisory, inspection checklist, and cleanup/reset.

Permits, approval status, fire watch, extinguishing resources, emergency shutdown, misfire procedure, abort criteria, and disposal.

Approval / completion criteria

No effect operates without documented approval and trained operator.

Safety zone is marked and protected.

Emergency shutdown and misfire procedure are rehearsed.

Synchronization rule: Coordinates with SAFE-01, STG-01, PWR-01, SM-01, and REP-02.

## SAFE-01 — Safety, Emergency, Contingency, and Show-Stop Plan

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Defines authority and actions when normal show operation is unsafe or impossible. | Production Manager and Venue Safety Authority are accountable; Stage Manager controls show communication within approved policy. | Venue emergency procedures; risk assessments; department failure plans; contacts; permits. |

Minimum required content

Emergency-stop and show-stop authority; exact terms for HOLD, ABORT/STOP, EVACUATE, RESUME, RESTART, and CANCEL.

Evacuation routes and assembly points; fire response; medical response; audience/performer injury; severe weather; security threat; power failure; audio/video/lighting-console failure; automation/platform/screen failure; costume delay; missing performer; effect misfire.

Who calls emergency services, who speaks to audience, who controls house lights/audio, who accounts for personnel, and who authorizes restart.

Incident/near-miss reporting, evidence preservation, notification, corrective action, and post-incident approval.

Approval / completion criteria

Venue and production procedures reconciled and approved.

All staff know stop authority and communications.

Emergency routes and equipment are physically verified.

Synchronization rule: Overrides normal execution when safety requires it; any resulting show change is propagated through CTRL-01 and Doc 1.

## COMMS-01 — Communications and Headset Plan

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Ensures every standby, confirmation, and emergency message reaches the correct person. | Stage Manager / Communications Lead. | Staff roster; department cue needs; venue systems; emergency plan. |

Minimum required content

Person/role, headset station, intercom channel, radio channel, call sign, cue-light assignment/meaning, and required listening periods.

Who receives each standby and confirmation; who may authorize a hold; radio discipline and priority words.

Backup method for failed intercom/radio, dead zones, spare batteries, and emergency communication procedure.

Approval / completion criteria

All positions tested from working locations.

Every safety-critical confirmation has a primary and backup path.

Synchronization rule: Referenced by SM-01, AUTO-01, FX-01, SAFE-01, and CONTACT-01.

## PWR-01 — Power Distribution and Shutdown Plan

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Provides an electrically safe, capacity-checked, and recoverable distribution design. | Technical Director / Qualified Electrician. | Venue power; equipment load data; stage plot; lighting/FX/AV plans. |

Minimum required content

Source panels, disconnects, voltages, phases, circuits, breaker ratings, calculated/verified loads, dimmers, relays, isolation, grounding/bonding, GFCI/RCD protection, distro, and cable types/routes.

Equipment-to-circuit assignment, spare capacity, generator/UPS or backup power where used, sequence for energization and shutdown, lockout/tagout authority, and fault response.

Inspection/test records and venue approval.

Approval / completion criteria

Loads remain within approved limits.

Cable routes and connectors are protected and suitable.

Shutdown and emergency isolation points are labeled and accessible.

Synchronization rule: Reconciles with STG-01, LX-02, AUD-01, VID-01, AUTO-01, and FX-01.

## VEN-01 — Venue Advance and House Interface Document

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Captures every venue fact and restriction that can alter production design or operation. | Production Manager with Venue Representative. | Venue technical package, site visit, contracts, local authority requirements. |

Minimum required content

Stage, wing, backstage, ceiling, trim, dock, door, corridor, elevator, and vehicle dimensions; load-in route and restrictions.

Power, rigging points/capacities, house audio/lighting/video, communications, dressing rooms, restrooms, storage, security, medical, fire systems, accessibility, staffing, labor rules, curfew, noise/sound limits, and house policies.

Permits, insurance/certificates, fire-watch requirements, prohibited effects/materials, audience advisories, parking, hospitality, waste, and emergency contacts.

Approval / completion criteria

Critical dimensions and capacities verified, not assumed.

Production plan conforms to venue rules or approved exceptions are documented.

Synchronization rule: Feeds STG-01, PWR-01, AUTO-01, FX-01, SAFE-01, SCHED-01, and CONTACT-01.

## SCHED-01 — Load-In, Rehearsal, Performance, and Load-Out Schedule

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Coordinates people, spaces, vehicles, and dependencies across the production day(s). | Production Manager. | Venue access/curfew; department estimates; rehearsal needs; labor/rest requirements. |

Minimum required content

Date, start/end, milestone, location, department, responsible owner, prerequisites, crew call, equipment arrival, setup sequence, soundcheck, focus, video test, costume/prop check, cue-to-cue, full run, doors, show, teardown, vehicle departure.

Meal/rest breaks, noise restrictions, shared-resource conflicts, contingency buffer, and hard deadlines.

Actual-versus-planned timing and reason for material deviation.

Approval / completion criteria

No impossible overlaps or missing dependencies.

All required personnel receive and acknowledge current schedule.

Synchronization rule: SM-02 presents the audience/show-facing summary; SCHED-01 is the detailed logistics authority.

## CHECK-01 — Department Preset, Pre-Show, Post-Show, and Shutdown Checklists

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Converts readiness and shutdown requirements into signed, repeatable action. | Stage Manager owns the master checklist; each department lead owns departmental sections. | All department plans; venue/safety requirements; Doc 1 pre/post checks. |

Minimum required content

Separate initialed sections for stage/scenery, automation, audio, lighting, video, wardrobe, props, instruments, FX, backstage, house/audience, communications, power, emergency equipment, and controlled-document revision.

Item, responsible person, required completion time, result, exception, corrective action, recheck, initials, and SM acceptance.

Post-show shutdown, safe-state, inventory, backup, damage/incident, maintenance, and release items.

Approval / completion criteria

No places call until required checks are accepted or an authorized documented exception exists.

Safety-critical failure blocks operation.

Synchronization rule: Draws requirements from every department document and feeds exceptions to REP-02/MAINT-01.

## CONTACT-01 — Contact Sheet and Responsibility Matrix

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Creates a single, current directory and responsibility map. | Production Manager. | Staffing list, venue contacts, emergency services, approval structure. |

Minimum required content

Name, role, organization, mobile, email, radio/call sign, working location, availability/call time, alternate, emergency contact, and privacy/distribution classification.

Approval authorities for artistic changes, safety holds, automation, effects, spending, schedule, venue interface, and document release.

RACI matrix—Responsible (does the work), Accountable (final owner), Consulted (provides input), Informed (must receive the result)—for key production decisions.

Approval / completion criteria

No critical role lacks a named primary and alternate.

Distributed in a privacy-conscious manner appropriate to the production.

Synchronization rule: Referenced by all documents; emergency contacts are mirrored in SAFE-01 only by controlled reference/version.

## REP-01 — Rehearsal Report

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Captures decisions and work generated by each rehearsal. | Stage Manager. | Rehearsal observations; notes from all departments; actual timing. |

Minimum required content

Rehearsal date/type, attendees, start/stop, sections run, active document revisions, planned versus actual timing, missed/late/changed cues, technical problems, performer/wardrobe/prop notes, injuries/near misses, decisions, assignments, owner, due date, and distribution.

Explicit indication of which notes are observations versus approved changes.

Approval / completion criteria

Every action has an owner and due date.

Approved changes enter CTRL-01 and affected documents; unapproved notes do not alter the show.

Synchronization rule: Feeds CTRL-01, MAINT-01, Doc 1, and all affected department documents.

## REP-02 — Daily Performance Report

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Creates the factual record of each performance and the action list for the next one. | Stage Manager. | Actual performance data; department reports; FOH/attendance; incident data. |

Minimum required content

Performance/date/venue, active revisions, actual house open, show start/stop, set start/stop, total runtime, audience count where applicable, late start and reason.

Cue problems, equipment failures, substitutions, performer notes, costume/prop issues, injuries, incidents, near misses, maintenance requests, approved changes made, people notified, and action required before next performance.

Owner, due date, priority, closure status, and links to incident/maintenance records.

Approval / completion criteria

Distributed promptly to the approved list.

Safety and maintenance actions are tracked to closure, not left only in narrative.

Synchronization rule: Updates MAINT-01 and CTRL-01; actual times never overwrite Doc 1 planned timing without approved revision.

## ASSET-01 — Show Asset, File, Version, Checksum, and Backup Manifest

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Prevents silent asset mismatch and makes show restoration possible. This is an added SSOT control required by the source documents’ repeated version, filename, backup, and recovery needs. | Production Manager coordinates; each department lead owns its assets. | All audio/video/console/show-control/configuration/document files. |

Minimum required content

Asset ID, department, purpose, related PGM/TECH/FIN ID, exact filename, format, software/hardware compatibility, version, revision/date, size, checksum/hash, primary location, local show location, backup locations, and owner.

Approval status, last verification date, restore-test result, dependency/plugin/font/codec requirements, and archival retention.

Clear designation of ACTIVE, BACKUP, SUPERSEDED, or ARCHIVED.

Approval / completion criteria

Every show-critical asset has an approved checksum and at least one tested backup.

Operators can restore the show environment from the manifest.

Synchronization rule: Referenced by AUD-01, LX-01/LX-02, VID-01, CTRL-01, and CHECK-01.

## MAINT-01 — Equipment Inspection, Maintenance, Damage, and Near-Miss Log

| Purpose and authority | Owner | Required inputs |
| --- | --- | --- |
| Tracks technical condition and corrective action beyond a single report. This closes the gap between checklists/performance reports and verified repair. | Technical Director / Production Manager. | Pre/post checks, rehearsal reports, performance reports, inspections, incidents. |

Minimum required content

Issue ID, date/time, equipment/item, symptom, severity, safety impact, discovered by, immediate action, tag-out status, responsible owner, parts/vendor, target date, repair details, test/verification, verifier, closure date, and recurrence linkage.

Damage and near-miss entries with conditions, contributing factors, corrective/preventive actions, and documents/cues affected.

Approval / completion criteria

Safety-critical defects remain blocked until authorized verification.

Recurring issues are identified and escalated.

Closure includes test evidence, not only a statement that repair was attempted.

Synchronization rule: Receives issues from CHECK-01, REP-01, REP-02, SAFE-01, and department inspections; closed changes may trigger CTRL-01 revisions.

# 6. Production Document Dependency and Build Order

1. Establish CTRL-01 and CONTACT-01.

2. Complete VEN-01 and SAFE-01 constraints.

3. Approve Doc 1 sequence, active timing profile, and known media versions.

4. Produce STG-01, PWR-01, LX-02, AUTO-01, and the initial ASSET-01 manifest.

5. Build AUD-01, LX-01, VID-01, DECK-01, WARD-01, PERF-01, PROP-01, FX-01, and COMMS-01.

6. Assemble SM-01 and CHECK-01 from the approved department documents.

7. Rehearse; issue REP-01; approve and propagate changes through CTRL-01.

8. Lock and distribute the performance revision; verify it through CHECK-01.

9. After each performance, issue REP-02 and update MAINT-01/CTRL-01 as required.

# 7. Change-Propagation Matrix

| Change originates in | Must be evaluated in | Minimum notification |
| --- | --- | --- |
| Doc 1 sequence, duration, or profile | SM-01, SM-02, AUD-01, LX-01, VID-01, WARD-01, PERF-01, CHECK-01, ASSET-01 | Producer/Director, PM, SM, all affected leads |
| Audio/video asset version | Doc 1 if duration changes; AUD-01/VID-01; ASSET-01; SM-01 | SM, department lead, PM |
| Stage layout or performer blocking | STG-01, DECK-01, AUTO-01, PERF-01, WARD-01, PROP-01, FX-01, SAFE-01, SM-01 | Director, SM, TD, affected leads |
| Automation/rigging or FX safety condition | AUTO-01/FX-01, SAFE-01, STG-01, SM-01, CHECK-01, VEN-01 as applicable | PM, SM, TD, venue/safety authority, all affected |
| Cue trigger or look | Department cue list, SM-01, REP-01, CTRL-01 | SM and affected operators |
| Personnel/responsibility/contact | CONTACT-01, COMMS-01, SM-01, CHECK-01, SCHED-01 | PM, SM, affected leads |
| Equipment defect or incident | MAINT-01, SAFE-01, REP-01/REP-02, CHECK-01, affected department plan | PM, TD, SM, safety authority |

# 8. Readiness Audit

| Audit question | Pass condition |
| --- | --- |
| Is there exactly one approved revision of every required document? | CTRL-01 shows APPROVED and obsolete copies are withdrawn. |
| Does every supporting cue reference a valid PGM/TECH/FIN ID? | No orphan or duplicate event identities. |
| Are all exact triggers, owners, and confirmations assigned? | No operational TBD remains in SM-01 or safety-critical department sheets. |
| Are media/configuration assets reproducible? | ASSET-01 has approved versions, checksums, backups, and restore tests. |
| Are stage, power, patch, rigging, FX, and venue constraints reconciled? | STG-01, PWR-01, LX-02, AUTO-01, FX-01, VEN-01, and SAFE-01 agree. |
| Are quick changes, performer routes, deck moves, and automation clearances conflict-free? | WARD-01, PERF-01, DECK-01, and AUTO-01 are jointly rehearsed. |
| Are failure, hold, abort, and recovery paths documented and tested? | SAFE-01 and department plans are approved and rehearsed. |
| Can the show be operated and restored from the controlled set? | A qualified operator can locate current documents/assets and follow them. |
| Are observations and defects tracked to closure? | REP-01/REP-02 actions appear in CTRL-01 or MAINT-01 with owners/status. |

# 9. Source Reconciliation and Expansion Record

| Source | Information retained | Useful completion added |
| --- | --- | --- |
| supportingdocuments01.txt | Detailed descriptions and fields for 17 supporting documents. | Controlled IDs, owners, dependencies, approval criteria, synchronization, and lifecycle. |
| supportingdocuments02.txt | Concise 21-document registry; unique DMX, power, venue, schedule, rehearsal, deck, performer, and equipment requirements. | Merged overlaps while preserving every unique operational category. |
| set01.txt and set02.txt | Pre/post checks, call conventions, technical-rehearsal needs, cue/safety concerns. | Document dependencies, readiness audit, asset/version controls, and maintenance/near-miss closure. |
| Synthesis additions | The sources did not fully define the governance mechanism needed for a lossless SSOT. | CTRL-01 lifecycle, immutable cross-references, change propagation, ASSET-01, MAINT-01, and pass/fail readiness criteria. |

# Appendix A — Blank Controlled-Document Register Row

| Document ID | Title | Owner | Approver | Status | Revision | Effective date | Doc 1 rev/profile | Primary location | Backup | Distributed to |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# Appendix B — Blank Change Record

| Change ID | Date | Origin | Affected ID/cue | Old value | New value | Reason | Risk/safety impact | Approved by | Propagated to | Verified by/date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |